## Tasks
S.No | Main Task | Task | Status | Estimated Hours | Start Date | End Date | Developer
Phase I (Target Date: 1st Week July)
1 | Dashboard View
1.1 |  | Dashboard UI development based on wireframe for desktop, tablet and mobile. | Completed |  |  |  | Pushpa
1.2 |  | Integrating Dashboard UI in existing code | Completed |  |  |  | Veenu/Pushpa
1.3 |  | Route impletmentation to render the Dashboard | Completed |  |  |  | Veenu
1.4 |  | Search Functionality on Dashboard screen based on Capability, Industry and Technology parameters | Completed |  | 2016-06-17 | 2016-06-20 | Suyash
1.5 |  | Search Functionality based on skillset in My Posts Section (Refresh the count for Applications received/Applications Offered/Applications rejected based on the selected skilset value) | Completed |  | 2016-06-17 | 2016-06-22 | Suyash
1.6 |  | Remove the notification and alert icon from recommended jobs section | Completed |  | 2016-06-17 | 2016-06-17 | Veenu
2 | Post A Job
2.1 |  | Post a Job UI development based on wireframe for desktop, tablet and mobile. | Completed |  |  |  | Pushpa
2.2 |  | Adding additional required field in the job schema | Completed |  | 2016-06-17 | 2016-06-20 | Veenu
2.3 |  | Functionality to post a job with additional fields, Job should be saved in database | Completed |  | 2016-06-20 | 2016-06-20 | Veenu
2.4 |  | Functionality to upload a document to a job, and save it in db | Completed |  |  |  | Pushpa
2.5 |  | Get the taxanomy structure for Industry and technology. Get the data for required software licence, country, location1/location2 and role | Completed |  |  | 2016-06-22 | Prahlad/Shilpi/Sharmila
2.6 |  | Backport the functionality to check the probability of getting work done based on the resources available on system. ( Parameter: Location, Lead time to mobilize, Mobility Flexibility, Role and career level) - UI Changes | Completed |  | 2016-06-20 | 2016-06-21 | Pushpa
2.7 |  | Remove- Modify guidelines | Completed |  | 2016-06-22 | 2016-06-22 | Pushpa/Prahlad
2.8 |  | Implementing routefor integration of Category, Industry and Technology specialization | Completed |  | 2016-06-23 | 2016-06-24 | Pushpa
3 | Job Application
3.1 |  | Job Application UI development for job poster with job status based on the wireframe(refer Slide6) | Completed |  | 2016-06-21 | 2016-06-22 | Veenu
3.2 |  | Job Application UI development for applicant to apply a job (Refer slide2) | Completed |  | 2016-06-16 | 2016-06-16 | Suyash
3.3 |  | Job Application UI development for applicant with application status | Completed |  | 2016-06-16 | 2016-06-20 | Veenu
3.4 |  | Rendering the page to display the attachments if any for the job | Completed |  | 2016-06-16 | 2016-06-16 | Suyash
3.4 |  | Functionality to download the document if clicked | Completed |  | 2016-06-16 | 2016-06-16 | Suyash
3.5 |  | Modification in route to integrate the job poster and job applicant UI | Completed |  | 2016-06-22 | 2016-06-22 | Veenu
3.6 |  | UI for Applications/Offered/Accepted/Complete UI development (Slide 7) (Job Poster View) as per the wireframe | Completed |  | 2016-06-22 | 2016-06-23 | Pushpa
3.7 |  | Integratng the UI for applications/offered/accepted | Completed |  | 2016-06-23 | 2016-06-24 | Veenu
3.8 |  | Route modification for an individual job. | Completed |  | 2016-06-23 | 2016-06-24 | Veenu
4 | Open Jobs / My Posts/ My Applications
4.1 |  | Open Jobs UI development to show all the open jobs (Refer Slide 1) | Completed |  | 2016-06-16 | 2016-06-17 | Pushpa
5 | Update Skill Profile
5.1 |  | Skill profile UI development based on the wireframe. | Completed |  | 2016-06-23 | 2016-06-27 | Suyash
5.2 |  | Add additional fields (Devices,Hardware and OS ), Working in client billable project(yes/no), Update the taxanomy structure for Industry and Technology) | Completed |  | 2016-06-24 | 2016-06-27 | Suyash
5.3 |  | Add new fields in User schema and save the user with new fields. | Completed |  | 2016-06-27 | 2016-06-27 | Suyash
6 | Admin
6.1 |  | UI to upload bench list data and verify the functionality to upload bench list data | Completed |  | 2016-06-27 | 2016-06-28 | Veenu
7 | Cross Browser
7.1 |  | Application should work in all browsers | Not Started
8 | Responsive
8.1 |  | Check the portal responsiveness | Not Started
9 | Login Screen
9.1 |  | Redesign the login screen as per the wireframe | Completed |  | 2016-06-27 | 2016-06-27 | Pushpa
10 | Data extraction from spreadsheet
10.1 |  | Extracting data from spreadsheet and creating an array | Completed |  | 2016-06-21 | 2016-06-21 | Suyash
10.2 |  | Converting the array to a json structure (required for jstree plugin) | Completed |  | 2016-06-23 | 2016-06-23 | Pushpa
11 | Server setup
11.1 |  | ec2 server setup, installating all the required software and setting up the application | Completed |  | 2016-06-22 | 2016-06-22 | Suyash
11.2 |  | SMTP server setup for emails | Completed |  | 2016-06-23 | 2016-06-27 | Suyash
Phase II- (Finish Date-TBD)
12 | Admin Dashboard
12.1 |  | Admin Dashboard UI to view All Jobs/Open Jobs/Completed Jobs/In Progress jobs/Red flag | Completed | 5 | 2016-07-15 | 2016-07-18 | Veenu
12.2 |  | Route Implementation to view all jobs, open jobs, completed jobs, in progress jobs | Completed | 10 | 2016-07-18 | 2016-07-18 | Veenu
12.3 |  | Integrate the functionality to populate red flag jobs | Completed | 4 | 2016-07-19 | 2016-07-19 | Veenu
12.4 |  | Email notification to the new bench list data uploaded | Completed |  | 2016-07-20 | 2016-07-20 | Suyash
13 | Post a Job
13.1 |  | Additional fields In UI and Job Schema: Trigger Email notification Date , Number of Applicant Required, | Completed |  | 2016-07-19 | 2016-07-19 | Pushpa
13.2 |  | Route changes to save the job and edit the job with additional fields | Completed |  | 2016-07-19 | 2016-07-19 | Pushpa
14 | Job Application
14.1 |  | Functionality to offer multiple applicants |  |  | 2016-07-19 | 2016-07-28 | Veenu
14.1.1 |  | Job schema modification to accept multiple offers | Completed | 1 | 2016-07-19 | 2016-07-19 | Veenu
14.1.2 |  | Job Offer functionality modification to except multiple offers (It should work for both single and multiple applicants) | Completed | 5 | 2016-07-20 | 2016-07-20 | Veenu
14.1.3 |  | Route changes to Job Application poster view to show correct count of offers. | Completed | 1 | 2016-07-21 | 2016-07-21 | Veenu
14.1.4 |  | Route changes to Job Application for both poster and applicant view to show the correct status of the job. | Completed | 8 | 2016-07-21 | 2016-07-21 | Veenu
14.1.5 |  | Modification to the route to view the Applications/Offered/Accepted view from job job detail page for poster. | Completed | 8 | 2016-07-22 | 2016-07-22 | Veenu
14.1.6 |  | Adding a new status(In progress) to the job, if job accepted by number of people required for the job. | Completed | 2 | 2016-07-22 | 2016-07-22 | Veenu
14.1.7 |  | Query modification to fetch Recommended jobs/My Posts/My Application | Completed | 3 | 2016-07-25 | 2016-07-25 | Veenu
14.1.8 |  | Check/modify all the filters in all the views | Completed | 5 | 2016-07-25 | 2016-07-26 | Veenu
14.1.9 |  | Verify the job apply functionality | Completed | 1 | 2016-07-26 | 2016-07-26 | Veenu
14.1.10 |  | If number of candidates required have accepted the job, then do not allow to offer or apply for a job. (Job poster view and job applicant view) | Completed | 4 | 2016-07-26 | 2016-07-26 | Veenu
14.1.11 |  | Job should be in open status until it get the required number of offers | Completed | 2 | 2016-07-25 | 2016-07-25 | Veenu
14.1.12 |  | Check the functionality of Reject Offer | Completed | 3 | 2016-07-27 | 2016-07-27 | Veenu
14.1.13 |  | Route modification for Dashbaord page | Completed | 8 | 2016-07-28 | 2016-07-28 | Veenu
14.1.14 |  | Route modification for Admin Dashboard | Completed | 8 | 2016-07-29 | 2016-07-29 | Veenu
14.1.15 |  | Modify the logic to mark job completed | Completed | 4 | 2016-07-28 | 2016-07-28 | Veenu
14.2 |  | On click of apply job, check if the applicant is working on chargeable client project.- UI | Completed |  | 2016-07-18 | 2016-07-18 | Pushpa
14.3 |  | On click of apply job, check if the applicant is working on chargeable client project. Backend changes | Not started
15 | User Profile
15.1 |  | User Profile UI development based on the wireframe Display user profile details with image, past work with ratings and comments, supervisor details, skill set, devices in hand, availability | In Progress | 4 hrs | 2016-07-28 | 2016-07-28 | Suyash/Pushpa | Note: UI work is pending. Backend work is done
15.2 |  | Route to render the user profile | Completed |  | 2016-07-19 | 2016-07-19 | Suyash
15.3
16 | Open Jobs / My Posts
16.1 |  | Trigger notifications for jobs that are not attended. Ways to trigger - Email Notification | Completed |  | 2016-07-27 | 2016-07-28 | Suyash
16.2 |  | Trigger notifications for jobs that are not attended. Ways to trigger - Add status alert icons against individual jobs | Completed |  | 2016-07-28 | 2016-07-29 | Suyash/prahlad/omar
17 | My Applications
17.1 |  | Add functionality for an applicant to provide status on a daily basis. Add start button and End button against each job. (Change label of button from Start -> work in progress, End button with a text field for adding comments onwork done on the day and submit) | Not Planned for Phase2 |  | TBD | TBD | TBD | Not planned for phase 2
18 | Discussion Forum
18.1 |  | Discussion Forum | Not Planned for Phase2 |  | TBD | TBD | Suyash,Veenu | Not planned for phase2
19 | New Changes from Prahlad /Saravana
19.1 |  | in Login page, provide 2 checkboxes a) do you want to post a job b) do you want to participate. If user selects option a, user will be redirected to post a job page. If user selects option b, user will be redirected to usual dashboard page. | Not Started | 4 hrs | 2016-07-28 | 2016-07-28 | Pushpa
19.2 |  | User profile page - Add one more row of category, industry and technology | Completed |  |  |  | Pushpa
19.3 |  | User profile page - industry should be mulitselect | Completed |  | 2016-07-14 | 2016-07-15 | Pushpa
19.4 |  | User profile page - remove mobility, speed to mobilise entries | Completed |  | 2016-07-14 | 2016-07-14 | Pushpa
19.5 |  | User profile page - devices should be multiselect, add one more option wearable entry under devices. Values for wearable would be provided by Prahlad | Completed |  | 2016-07-15 | 2016-07-15 | Pushpa
19.6 |  | User profile page - make country, location 1 and 2 as single select | Completed |  | 2016-07-14 | 2016-07-14 | Pushpa
19.7 |  | Post job - check whether email is triggered when a job is posted. Email should be sent to job poster and all the suitable resources available | In Progress | 4 hrs | 2016-08-01 | 2016-08-01 | Suyash
19.8 |  | Signup and Login:Client side validation for signup and login | Completed |  |  |  | Suyash
19.9 |  | Add Confirm Password in signup | Completed |  | 2016-07-27 | 2016-07-27 | Suyash
19.11 |  | Add utility to forewer run the node server | Completed |  | 2016-07-28 | 2016-07-28 | Suyash
19.12 |  | Prepare Server Doc for restart the server | Completed |  | 2016-07-27 | 2016-07-17 | Suyash
20 | Cross Browser
20.1 |  | Application should work in all browsers(Chrome, FF and ie10+). Testing and fixing UI issues | Completed | 36 hrs | 2016-07-20 | 2016-07-25 | Pushpa
21 | UI Changes and UI Responsive
21.1 |  | Check the portal responsiveness | Completed | 27 hrs | 2016-07-27 | 2016-08-01 | Pushpa
21.2 | Application Fonts | Converted ttf to different font formats to support cross browser. Embedding fonts and testing in all browsers. | Completed | 2 hrs | 2016-07-26 | 2016-07-26 | Pushpa
21.3 | Application Logo | Add logo for mobile and desktop | Completed | 1 hr | 2016-07-27 | 2016-07-27 | Pushpa
21.4 | Layout update | UI for Settings from dropdown menu | Completed | 1hr | 2016-07-27 | 2016-07-27 | Pushpa
21.5 |  | Change Settings to Personal Preferences | Completed |  | 2016-08-01 | 2016-08-01 | Pushpa
21.6 | Layout update | Layout update - UI for FAQ from drop down menu | Completed | 1hr | 2016-07-27 | 2016-07-27 | Pushpa
21.7 |  | Update content for FAQ | Not started
26 | Issue List
26.1 | Profile pic dropdown | The background should be not transparent. | Completed |  | 2016-07-28 | 2016-07-28 | Pushpa
26.2 | Admin Dashboard | Add breakup of open jobs (normal and risk jobs) under Doughnut | Completed |  | 2016-07-29 | 2016-07-29 | Veenu
26.3 | Dashboard | Changes in recommended jobs list: hardcoded values of level, no of positions, positions left should be changed with actual values | Completed |  | 2016-08-01 | 2016-08-01 | Veenu
26.4 | My Posts/ My Applications | Changes in recommended jobs list: hardcoded values of level, no of positions, positions left should be changed with actual values | Completed |  | 2016-08-01 | 2016-08-01 | Veenu
26.5 | Admin Dashboard | Changes in recommended jobs list: hardcoded values of level, no of positions, positions left should be changed with actual values | Completed |  | 2016-08-02 | 2016-08-02 | Veenu
26.6 |  | Keep menu open | Completed |  | 2016-08-01 | 2016-08-01 | Pushpa
26.7 |  | Reduce the size of banner image in dashboard | Completed |  | 2016-08-01 | 2016-08-01 | Pushpa
26.8 |  | Move Description field to top in Post job and Apply job page | In Progress |  |  |  | Pushpa
26.9 | Signup | Add an additional field: confirm password | Completed |  |  |  | Suyash
26.1 | Post a Job | Post a job section put star for all the mandatory fields | Completed |  |  |  | Pushpa
26.11 | Post a Job | Industry field instead of Not Applicable change it to Cross Industry | Completed |  |  |  | Pushpa
| Post a Job | Issue to Show the correct bench size in post a job section, and on click of Available bench user show the correct number of user. | Completed |  | 2016-08-02 | 2016-08-02 | Veenu

## IssueList
S.No | Issue | Status | Developer
Update User profile
1 | Interface change: Add a top header above Category: "Choose your skillset based on category, industry and technology" | Completed | Suyash
2 | Add Additional rows with top heading as "Would you like to participate in other categories too? And add Category, industry and technology ( Add two rows for this) | Completed | Suyash
3 | Remove roles from user profile screen | Completed | Suyash
4 | Location field should look like the way we have it in Post a Job section (Country/Location1/location2) | Completed | Suyash
5 | Option For the user to add multiple devices. Change the header of devices required. | Planned for Phase2 | Suyash
6 | Add extra field to capture network provider | Completed | Suyash
7 | Do you have any desktop/laptop assigned (yes/no) | Planned for Phase2 | Suyash
Dashboard View
8 | Rename the My post (donut section): to "Jobs/tasks posted by me" | Completed | Suyash
9 | Change the filter criteria from By skillset to By JObtitle in MyPost section. And accordingly the search should work. | Completed | Suyash
10 | Search option the top By skillset: make it autocomlete. | Completed | Suyash
11 | Search error message should be little highlighted. It is not visible | Completed | Suyash
12 | Once the search is clicked, myApplication and Myposts Donut section should get collapsed and the recommended jobs section should come at the top. | Completed | Suyash
13 | Hide open jobs from the dashboard left side menu: | Completed | Veenu
Job Application
14 | In job application poster view: Put a label on top of Application()/Offered()/Accepted(). "Click below links to view the applicants": | Completed | Veenu
15 | Job Application: Applications() view: provide a hyperlink on the applicant name which should allow the user to open lync window and chat with the person. | Planned for phase 2
Post a Job
16 | Reword Chargeable WBS to "Reward" with values as "WBSE and CP points" | Completed | Veenu
17 | In urgent job checkbox remove "Must be done today" | Completed | Veenu
18 | Hide the Opportunity checkbox | Completed | Veenu
19 | In Technology: parent node should not be allowed to checked, only child nodes can be selected | Completed | Pushpa
20 | Instead of software license and access required fields add below fields; Software required, Would you provide licence, would you provide access, would you provide hardware. | Completed | Pushpa
21 | Add data to country, location1 and location2 | Completed | Veenu
22 | Role should be removed. | Completed | Veenu
23 | In Right side Location, prepopulate data from location2 field. | Completed | Veenu
24 | Need to check with Omar about "Leadtime to Mobilize" and "Mobility Flexibility" Applicability of these fields.
Apply Job Modal
25 | Change the guidelines. (Change Operations to technology): | Completed | Veenu
Others
26 | In Dashboard View: if no data for Myapplications or Myposts for logged in user, show tha blank donut. | Completed | Pushpa
27 | In Dashboard Search By Skillset section, functionality to do multiple selection
28 | In Open jobs/MyPosts/Myapplication, when filter is applied to jobs, in the rendered view filter disappears. | Completed | Veenu
29 | Apply Job button should not come if the logged in user has already applied for that job. (For OpenJobs) | Completed | Veenu
30 | Apply Job button should not come for jobs displayed in MyApplications section and MyPosts section. | Completed | Veenu
31 | In Dashboard View: My Posts Donut chart values need to be verified. | Completed | Veenu
32 | Edit job is not pre-populating the new added fields. | Completed | Pushpa
1 | Trigger Email notification date..must not be greater than the start date.
2 | If no Software required entered by user…then y Software Access and hardware access fields are required
3 | For the userprofile pemalink…if clicked directly and user is not logged in…it ask for log in…and after that it redirects to the dashboard page….it should redirect to the user profile page
4

## CompletedFeatures
Feature ID | Feature Scope | Description | Release | Status | Estimated Effort | Start Date | End Date | Assignee
12.1 | Admin Dashboard | Admin Dashboard UI to view All Jobs/Open Jobs/Completed Jobs/In Progress jobs/Red flag | 0.2 | Completed | 5 | 2016-07-15 | 2016-07-18 | Veenu
12.2 | Admin Dashboard | Route Implementation to view all jobs, open jobs, completed jobs, in progress jobs | 0.2 | Completed | 10 | 2016-07-18 | 2016-07-18 | Veenu
12.3 | Admin Dashboard | Integrate the functionality to populate red flag jobs | 0.2 | Completed | 4 | 2016-07-19 | 2016-07-19 | Veenu
12.4 | Admin Dashboard | Email notification to the new bench list data uploaded | 0.2 | Completed |  | 2016-07-20 | 2016-07-20 | Suyash
13.1 | Post a Job | Additional fields In UI and Job Schema: Trigger Email notification Date , Number of Applicant Required, | 0.2 | Completed |  | 2016-07-19 | 2016-07-19 | Pushpa
13.2 | Post a Job | Route changes to save the job and edit the job with additional fields | 0.2 | Completed |  | 2016-07-19 | 2016-07-19 | Pushpa
14.1 | Job Application | Functionality to offer multiple applicants | 0.2 |  |  | 2016-07-19 | 2016-07-28 | Veenu
14.1.1 | Job Application | Job schema modification to accept multiple offers | 0.2 | Completed | 1 | 2016-07-19 | 2016-07-19 | Veenu
14.1.2 | Job Application | Job Offer functionality modification to except multiple offers (It should work for both single and multiple applicants) | 0.2 | Completed | 5 | 2016-07-20 | 2016-07-20 | Veenu
14.1.3 | Job Application | Route changes to Job Application poster view to show correct count of offers. | 0.2 | Completed | 1 | 2016-07-21 | 2016-07-21 | Veenu
14.1.4 | Job Application | Route changes to Job Application for both poster and applicant view to show the correct status of the job. | 0.2 | Completed | 8 | 2016-07-21 | 2016-07-21 | Veenu
14.1.5 | Job Application | Modification to the route to view the Applications/Offered/Accepted view from job job detail page for poster. | 0.2 | Completed | 8 | 2016-07-22 | 2016-07-22 | Veenu
14.1.6 | Job Application | Adding a new status(In progress) to the job, if job accepted by number of people required for the job. | 0.2 | Completed | 2 | 2016-07-22 | 2016-07-22 | Veenu
14.1.7 | Job Application | Query modification to fetch Recommended jobs/My Posts/My Application | 0.2 | Completed | 3 | 2016-07-25 | 2016-07-25 | Veenu
14.1.8 | Job Application | Check/modify all the filters in all the views | 0.2 | Completed | 5 | 2016-07-25 | 2016-07-26 | Veenu
14.1.9 | Job Application | Verify the job apply functionality | 0.2 | Completed | 1 | 2016-07-26 | 2016-07-26 | Veenu
14.1.10 | Job Application | If number of candidates required have accepted the job, then do not allow to offer or apply for a job. (Job poster view and job applicant view) | 0.2 | Completed | 4 | 2016-07-26 | 2016-07-26 | Veenu
14.1.11 | Job Application | Job should be in open status until it get the required number of offers | 0.2 | Completed | 2 | 2016-07-25 | 2016-07-25 | Veenu
14.1.12 | Job Application | Check the functionality of Reject Offer | 0.2 | Completed | 3 | 2016-07-27 | 2016-07-27 | Veenu
14.1.13 | Job Application | Route modification for Dashbaord page | 0.2 | Completed | 8 | 2016-07-28 | 2016-07-28 | Veenu
14.1.14 | Job Application | Route modification for Admin Dashboard | 0.2 | Completed | 8 | 2016-07-29 | 2016-07-29 | Veenu
14.1.15 | Job Application | Modify the logic to mark job completed | 0.2 | Completed | 4 | 2016-07-28 | 2016-07-28 | Veenu
14.2 | Job Application | On click of apply job, check if the applicant is working on chargeable client project.- UI | 0.2 | Completed |  | 2016-07-18 | 2016-07-18 | Pushpa
15.2 | User Profile | Route to render the user profile | 0.2 | Completed |  | 2016-07-19 | 2016-07-19 | Suyash
15.3 | User Profile |  | 0.2
16.1 | Open Jobs / My Posts | Trigger notifications for jobs that are not attended. Ways to trigger - Email Notification | 0.2 | Completed |  | 2016-07-27 | 2016-07-28 | Suyash
16.2 | Open Jobs / My Posts | Trigger notifications for jobs that are not attended. Ways to trigger - Add status alert icons against individual jobs | 0.2 | Completed |  | 2016-07-28 | 2016-07-29 | Suyash/prahlad/omar
19.2 | User Profile | User profile page - Add one more row of category, industry and technology | 0.2 | Completed |  |  |  | Pushpa
19.3 | User Profile | User profile page - industry should be mulitselect | 0.2 | Completed |  | 2016-07-14 | 2016-07-15 | Pushpa
19.4 | User Profile | User profile page - remove mobility, speed to mobilise entries | 0.2 | Completed |  | 2016-07-14 | 2016-07-14 | Pushpa
19.5 | User Profile | User profile page - devices should be multiselect, add one more option wearable entry under devices. Values for wearable would be provided by Prahlad | 0.2 | Completed |  | 2016-07-15 | 2016-07-15 | Pushpa
19.6 | User Profile | User profile page - make country, location 1 and 2 as single select | 0.2 | Completed |  | 2016-07-14 | 2016-07-14 | Pushpa
19.8 | Signup and Login | Signup and Login:Client side validation for signup and login | 0.2 | Completed |  |  |  | Suyash
19.9 | Signup and Login | Add Confirm Password in signup | 0.2 | Completed |  | 2016-07-27 | 2016-07-27 | Suyash
19.11 | Signup and Login | Add utility to forewer run the node server | 0.2 | Completed |  | 2016-07-28 | 2016-07-28 | Suyash
19.12 | Signup and Login | Prepare Server Doc for restart the server | 0.2 | Completed |  | 2016-07-27 | 2016-07-17 | Suyash
20.1 | Cross Browser | Application should work in all browsers(Chrome, FF and ie10+). Testing and fixing UI issues | 0.2 | Completed | 36 hrs | 2016-07-20 | 2016-07-25 | Pushpa
21.1 |  | Check the portal responsiveness | 0.2 | Completed | 27 hrs | 2016-07-27 | 2016-08-01 | Pushpa
21.2 | Application Fonts | Converted ttf to different font formats to support cross browser. Embedding fonts and testing in all browsers. | 0.2 | Completed | 2 hrs | 2016-07-26 | 2016-07-26 | Pushpa
21.3 | Application Logo | Add logo for mobile and desktop | 0.2 | Completed | 1 hr | 2016-07-27 | 2016-07-27 | Pushpa
21.4 | Layout update | UI for Settings from dropdown menu | 0.2 | Completed | 1hr | 2016-07-27 | 2016-07-27 | Pushpa
21.5 | Layout update | Change Settings to Personal Preferences | 0.2 | Completed |  | 2016-08-01 | 2016-08-01 | Pushpa
21.6 | Layout update | Layout update - UI for FAQ from drop down menu | 0.2 | Completed | 1hr | 2016-07-27 | 2016-07-27 | Pushpa

## FeaturesInProgress
Feature ID | Feature Scope | Description | Release | Status | Estimated Effort | Start Date | End Date | Assignee
15.1 | User Profile | User Profile UI development based on the wireframe Display user profile details with image, past work with ratings and comments, supervisor details, skill set, devices in hand, availability | 0.2 | completed | 4 hrs | 2016-07-28 | 2016-07-28 | Suyash/Pushpa | Note: UI work is pending. Backend work is done
19.7 | Post a Job | Post job - check whether email is triggered when a job is posted. Email should be sent to job poster and all the suitable resources available | 0.2 | completed | 4 hrs | 2016-08-01 | 2016-08-01 | Suyash
28 | SSO integration | SSO integration |  | In progress |  |  |  | Omar/Suyash
29 | Code review | code review of entire application |  | In progress | 18 hrs | 2016-08-08 | 2016-08-09 | Suyash
30 | Documentation | Documentation |  | In progress |  |  |  | Veenu
31 | Support to testing team | Support to testing team |  | In progress |  |  |  | Pushpa

## PlannedFeatures
Feature ID | Feature Scope | Description | Release | Status | Estimated Effort | Start Date | End Date | Assignee
17.1 | My Applications | Add functionality for an applicant to provide status on a daily basis. Add start button and End button against each job. (Change label of button from Start -> work in progress, End button with a text field for adding comments onwork done on the day and submit) | 0.3 | Not Planned for Phase2 |  | TBD | TBD | TBD | Not planned for phase 2
18.1 | Discussion Forum | Discussion Forum | 0.3 | Not Planned for Phase2 |  | TBD | TBD | Suyash,Veenu | Not planned for phase2
14.3 | Job Application | On click of apply job, check if the applicant is working on chargeable client project. Backend changes | 0.2 | Not started
19.1 | Login | in Login page, provide 2 checkboxes a) do you want to post a job b) do you want to participate. If user selects option a, user will be redirected to post a job page. If user selects option b, user will be redirected to usual dashboard page. | 0.2 | completed | 4 hrs | 2016-07-28 | 2016-07-28 | Somya
21.7 | Layout update | Update content for FAQ | 0.2 | Not started
14.1 | Job Application | Functionality to offer multiple applicants | 0.2 | completed |  | 2016-07-19 | 2016-07-28 | Veenu
15.3 | User Profile |  | 0.2
27 | UI update for pages in Admin
27.1 | View bench | UI needs to be developed once wireframe is ready |  | Not started
27.2 | Upload | UI needs to be developed once wireframe is ready |  | Not started

## CompletedIssues
Issues ID | Feature Scope | Description | Release | Status | Estimated Effort | Start Date | End Date | Assignee
26.1 | Profile pic dropdown | The background should be not transparent. | 0.2 | Completed |  | 2016-07-28 | 2016-07-28 | Pushpa
26.2 | Admin Dashboard | Add breakup of open jobs (normal and risk jobs) under Doughnut | 0.2 | Completed |  | 2016-07-29 | 2016-07-29 | Veenu
26.3 | Dashboard | Changes in recommended jobs list: hardcoded values of level, no of positions, positions left should be changed with actual values | 0.2 | Completed |  | 2016-08-01 | 2016-08-01 | Veenu
26.4 | My Posts/ My Applications | Changes in recommended jobs list: hardcoded values of level, no of positions, positions left should be changed with actual values | 0.2 | Completed |  | 2016-08-01 | 2016-08-01 | Veenu
26.5 | Admin Dashboard | Changes in recommended jobs list: hardcoded values of level, no of positions, positions left should be changed with actual values | 0.2 | Completed |  | 2016-08-02 | 2016-08-02 | Veenu
26.6 |  | Keep menu open | 0.2 | Completed |  | 2016-08-01 | 2016-08-01 | Pushpa
26.7 |  | Reduce the size of banner image in dashboard | 0.2 | Completed |  | 2016-08-01 | 2016-08-01 | Pushpa
26.8 |  | Move Description field to top in Post job and Apply job page | 0.2 | Completed |  |  |  | Pushpa
26.1 | Post a Job | Post a job section put star for all the mandatory fields | 0.2 | Completed |  |  |  | Pushpa
26.11 | Post a Job | Industry field instead of Not Applicable change it to Cross Industry | 0.2 | Completed |  |  |  | Pushpa
26.12 | Post a Job | Issue to Show the correct bench size in post a job section, and on click of Available bench user show the correct number of user. | 0.2 | Completed |  | 2016-08-02 | 2016-08-02 | Veenu
26.13 | Login | Login page don’t have signup page | 0.2 | Completed |  | 2016-08-03 | 2016-08-03 | Somya
26.14 | Post job and Job details page | Move Description field to top in Post job and Apply job page | 0.2 | completed |  |  |  | Pushpa

## IssuesPlannedInProgress
Issue ID | Feature Scope | Description | Release | Status | Estimated Effort | Start Date | End Date | Assignee | Comments
26.15 | Signup | Signup page looks more like login page, no typical fields of registration | 0.2 | Planned |  |  |  |  | Waiting for wire-frame and style guide
26.16 | Signup | User name should be vaild email id, - currently it takes everything | 0.2 | Planned |  |  |  |  | Need to discuss with need on the estimate
26.17 | Signup | Using other person email id, with new password , we can signup – impersonating others | 0.2 | Planned |  |  |  |  | Need to discuss with need on the estimate
26.18 | Signup | Duplicate signup accepted | 0.2 | Planned |  |  |  |  | Its not replicable
|  | Email id to be captured as part of registration and email to be triggered registration confirmation | 0.2 | Planned |  |  |  |  | Need to discuss with need on the estimate
26.19 | Issues reported by Saba on 5th Aug
26.19.1 | Login page | Do not provide user name and password and click submit button, system it's showing "Please enter your username, Please enter your password"; Alert message color should be change to visible colour. [Ref: Screenshot] |  | completed
26.19.2 | Login page | System fails to refresh the old alert message. [Ref: Screenshot] |  | completed
26.19.3 | Personal preference | It's not working properly. | [6 empty] | Need clarification on the issue
26.19.4 | FAQ | There is no exit buttons. If the user wants to come out that option need to click back space and then only user can see dashboard page. Make it as unique alignment like other menus. | [6 empty] | Currently when we click on logo we are redirecting to dashboard. Waiting for new wireframe
26.19.5 | X mark | X mark is displaying in top left corner of the page. Make this into rename or like relevant information need to be changed. [Ref: Screenshot] |  | completed | 1
26.19.6 | Dashboard page | In Dashboard page, user did not provide any inputs and click search button system is showing alert message as " Please enter in serach box or select atleast one skill." Alert message color should be change to visible colour. |  | completed
26.19.7 | Skill profile page | First time user try to update skills given some fields and click submit button system it's showing "Alert! Your Liquid Work Force skills profile is not complete." But Missing field should be highlighted. And then only user can handle easily. [Ref: Screenshot] |  | completed
26.19.8 | Dashboard page | In the dashboard page, Texts are displaying out of the frames. [Ref: Screenshot] | [6 empty] | Not replicable
26.19.9 | Dashboard page | Once we click the 'Apply job' button system its showing one frame box. In the frame user did not provide any inputs and click 'Apply' button system is accepting without any alert message. In this frame there is no mandatory field required? Please clarify. | [6 empty] | Not started. As discussed in call for now we are leaving it as it is.
26.19.10 | Entire application | Copyrights should not be overlapped. Now it's overlapping with the borders. Right side alignment need to be done. [Ref: Screenshot] | [6 empty] | completed. As discussed in call for now we are leaving it as it is.
26.19.11 | Post a job | Without select any filed and click 'Post job' button system it's showing some is highlighting for the mandatory field. For some other fieds are missing to highlight. [Ref: Screenshot] |  | completed
26.2 | Multi-select dropdown height issue | Across application |  | completed
26.21 | Issues reported on 9th August
26.21.1 | User Profile Page | Page is getting refreshed and the entered details are missing on leaving Technology field as blank and clicking on submit button. |  | not replicable
26.21.2 | My Applications | Selected Filter is not persisting and is changing to default value on selecting any filter |  | completed
26.21.3 | My Posts | Selected Filter is not persisting and is changing to default value on selecting any filter |  | completed
26.21.4 | My Posts - Edit Job | On clicking edit job, entered Category , Technology details are missing. |  | completed
26.21.5 | Dashboard - Jobs/Tasks Posted by Me | On deleting the post, count is not getting reduced on dashboard for Jobs/Tasks Posted by Me and Open is still displayed same |  | completed | 4
26.21.6 | Login page | Button has to to consistent across the application |  | completed
26.21.7 | Login page | Font Size and Color not matching with Application |  | completed
26.21.8 | Registration | Change Username label to Accenture Enterprise Id |  | completed
26.21.9 | Post a job | There is no space between label and Input fields |  | completed
26.21.10 | Job details page | Clicking on job from My Post redirected to login page instead of Job description page |  | completed
27.1 | Login page | Align Logo with proper spacing |  | completed
27.2 | Login page | Sign up link color has to consitent with application |  | completed
27.3 | Dashboard - Jobs/Tasks Posted by Me | Error message color need to be change for search in dashboard |  | completed
27.4 | Dashboard - Jobs/Tasks Posted by Me | Font should be bold for Position count and Position Left in Job section |  | completed | 0.5
27.5 | Across Apllication | Breadcrumb has to be added across application |  | completed
27.6 | User Profile Page | User profile picture has to be added |  | not started |  |  |  |  | Need to disscus with the team for estimation
27.7 | User Profile Page | Remove underline to the title text and add ‘214d72’ color |  | completed | 0.5
27.8 | FAQ | FAQ is not as per the designed template |  | completed
27.9 | Upload Opportunities | Page needs to be designed in terms of alignment and spacing |  | not started | 1 | Need to confirm with Veenu/Omar if we are using this else we need to remove from user profile dropdown
28.1 | View Bench | Page is not as per the desined template |  | completed | 9
28.2 | Admin access - Upload members list | In Upload members list page - Alignment should be proper. [Ref: Screenshot] |  | completed | 1
28.3 | Admin access - Upload members list | In Upload members list page - without select anything and click submit button system redirects to 'not found' page. [ Ref: Screenshot] |  | Completed | 1
28.4 | Admin access - Upload members list | Which format file should be supported into this page. Can you please clarify. |  | Completed | 1 |  |  |  | It supports only csv format
28.5 | Admin access - Upload opportunities | In Upload opportunities page - Alignment should be proper. [Ref: Screenshot] |  | not started |  | Need to confirm with Veenu/Omar if we are using this else we need to remove from user profile dropdown
28.6 | Admin access - Upload opportunities | In Upload opportunities page - without select anything and click submit button system redirects to 'not found' page. [ Ref: Screenshot] |  | not started |  | Need to confirm with Veenu/Omar if we are using this else we need to remove from user profile dropdown
28.7 | Admin access - Upload opportunities/Upload members list | In Upload opportunities/Upload members list pages - System does not throw success or failure alert message after upload the opportunities or member list. Check this major functionality. |  | completed | 1
28.8 | Dashboard page | Alignment should be proper. [Ref: Screenshot] |  | not started
28.9 | Entire application | Menu heading format should be same format in entire application. |  | completed
29 | User Profile Page | Replacing Technology with Multi select |  | In Progress | 9
29.1 | Dashboard > My Posts > Job Application | In the job application page - Click 'Flag job' option that frame is overlapping into the texts [ Ref: Screenshot] |  | not started
29.2 | Dashboard > My Posts > Job Application | In the job application page - Click Admin access - Email bench link system is showing some frame without close button. This frame also not relevant information. Can you please check. [ Ref: Screenshot] |  | not started
29.3 | Dashboard page | Jobs/Tasks Posted by Me count should be displayed near the filed. Now system displayed the value too long. User will be confused. [Ref: Screenshot] |  | not started
29.4 | Personal preference | If you click the information link system should be move into the correct navigation and should be stable that particular place. But now system is jerking. Check this functionality |  | not started
29.5 | Entire application | Font Size should be uniformity in entire application. [ Ref: Screenshot] |  | not started
29.6 | Entire application | URL link should be relevant matches to the menus. Now system is showing not uniform. For example if we click Dashboard , url should be https://liquidforce.accenture.com/dashboard. This is the correct format. Other 3 menus are wrong I,e https://liquidforce.accenture.com/apps, https://liquidforce.accenture.com/jobs/mine, https://liquidforce.accenture.com/job/new... |  | not started
29.7 | View all jobs page | Open not attended showing 24 value. Once we click open not atend tab system shows the values as 17 only. Based on the historical values should be reflected into all tabs. Check other tabs also. [Ref: Screenshot] |  | not started
29.8 | View all jobs page | Can you please explain anyone functionality of this page? I think its displayed count values as wrong. |  | not started
29.9 | Edit job | IF the user trying to edit the job system is showing "forbidden' text alone. {Ref: Screenshot} |  | not started
30 | Delete job | If we try to delete the job, frame cancel and delete should be equal format. [Ref: Screenshot] |  | not started
30.1 | Delete job | System does not allow to delete the job even user click the delete job button. System fails to delete the job. |  | not started
30.2 | Delete job | Sometimes system fails to display the cancel and delete button [Ref: Screenshot] |  | not started